## Gantt Chart - Manual Duration
Task Name | Start Date | End Date | Duration (Days) | Days Complete | Days Remaining | Percent Complete | Start Date in Number Form | 43169
Sprint 1: Ready for Project 1.1 Learn Java 1.2 Install IDE and JAVA environment | 2018-03-10 | 2018-03-15 | 5 | 5 | 0 | 100%
Sprint 2: Identify Project 2.1 Understand Project requirement 2.2 Prepare Class Diagram 2.3 Prepare Use Case Diagram | 2018-03-16 | 2018-03-21 | 5 | 5 | 0 | 100%
Sprint 3: Implementation of Project 3.1 Data IO 3.2 UI | 2018-03-22 | 2018-03-30 | 8 | 8 | 0 | 100%
Sprint 4: Implementation of Project 4.1 Filtering Data 4.2 Graph Plotting | 2018-04-03 | 2018-04-11 | 8 | 8 | 0 | 100%
Sprint 5: Implementation of Project 5.1 Spliting of data 5.2 Graph Transformation | 2018-04-15 | 2018-04-25 | 10 | 10 | 0 | 100%
Sprint 6: Debug and testing 6.1 Unit Testing 6.2 JavaDoc 6.3Debug | 2018-04-27 | 2018-05-03 | 6 | 6 | 0 | 100%
[7 empty] | Key: | Calculated Cell | Manual Entry Cell
[8 empty] | These cells will be automatically calculated based on the inputs on other cells. | These cells require manual input so the calculated cells have data to work with.